## CMC Timeline
|  |  | Product Name | Pharm and Biologics Development Plan and Timeline
|  | Start Date | 2013-11-13 | Systematic Product Development for Biologics and Pharmacuticals |  |  |  |  | CMC Leader |  |  |  |  | All dates are completion dates. The activity will be started in advance to complete the activity by that date.
|  | 2013 | [7 empty] | 2014 | [51 empty] | 2014
Ownership and Accountability | Development Activities | Pre-Clinical Activities Product and System Design | [7 empty] | Phase I Level Work - Begin Parameter Design (product and Process understanding) | [12 empty] | Phase II Level Work - Complete Parameter Design and Tolerance Design, Pre-Validation | [20 empty] | Phase III Level Work - Robust Design, Scale, Tech Transfer and Validation | [18 empty] | Continous Process Validation and Control
CMC CoreTeam |  |  | Establish Target Product Profile and Define Critical Quality Attributes | [7 empty] | Reviews and Updates on all Clinical risk assessments. | [12 empty] | Updates on all Clinical and Phase I risk assessments. | [20 empty] | Defined Unit Operations and process flow
|  |  | Clinical Risk Assessment | [7 empty] | Detailed process maps and high level risk assessments | [12 empty] | Unit operation DOEs | [20 empty] | Scale up parameters and transfer approach
|  |  | Process and Method Risk Assessment | [7 empty] | Detailed assay process maps and risk assessments | [12 empty] | Line segment DOEs | [20 empty] | Key raw materials and raw material variation studies
|  |  | Material Selection Risk Assessment | [7 empty] | Screening studies on materials, columns, excipients | [12 empty] | Full line runs and setpoint validation | [20 empty] | Analytical methods validation reports and ATP models
|  |  | TPP and CQA Risk Assessment | [7 empty] | Initial Critical Method Risk Assessment | [12 empty] | Process and method optimization and design space with respect to CQAs and CPPs. | [20 empty] | Batch variation studies
|  |  | PreClinical QRM Report and associated risk reduction activities | [7 empty] | Facility, method, and/or process transfer risk assessment | [12 empty] | Critical parameter identification and control plan for process | [20 empty] | Model validation (actual versus predicted)
|  |  | Equipment selection | [7 empty] | QRM Report and associated risk reduction activities | [12 empty] | Critical parameter control plan for analytical method | [20 empty] | Process model (profiler and contour profiler for design space) and effect size, % of tolerance and variation and Critical Process Parameters (CPPs)
|  |  | Cell Line Development and Material and Excipient selection | [7 empty] | Begin Development in final form | [12 empty] | Facility, method, and/or process transfer risk assessment | [20 empty] | Set all process specification limits for proven acceptable ranges (PARs)
|  |  | Process design | [7 empty] | Equipment variation at set point (NORs) (temperature, pressure, speed etc.) | [12 empty] | QRM Report and associated risk reduction activities | [20 empty] | All product specification limits (CQAs and Assays)
|  |  |  | Required analytical methods (what by when) | [19 empty] | Simulation and margin analysis from set points | [20 empty] | Process control strategy and design (SPC/PAT control loops, key assays and inspection points)
|  |  |  | Dev location strategy | [19 empty] | Capability analysis | [20 empty] | Validation plan
|  |  |  | Initial system test | [19 empty] | Stabiity analysis | [20 empty] | Validation report
Activity Owner
Analytical Sciences | Method Identification
Method Development (process, risk and DOE)
Standards and controls
Precision/Accuracy
Linearity
LOD/LOQ
Intra lab precision
Intermediate precision
Transfer package, ATP profiler
Equivalence testing/Transfer Results
Reports
Activity Owner
Development Timeline |  | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
 | time axis 2013-11-13 to 2015-12-30
Process Sciences and Formulation (DS/DP) | Process design and flow maps
Materials and Equipment Definition
High Level Risk Assessment
Low level Risk Assessment-Pre DOE
Screening Studies and preliminary runs
Scale Strategy
Characterization DOEs and Set Points
DS and DP stability evaluation
Process Models and Set Points, Design Space
Release Spec Limits and Process Capability
Process Controls
Process Validation and transfer
Reports
Activity Owner:
Needed Resources and Sample Sizes | Scientific and Engineering FTEs
Materials
Equipment
Sample Size
Lab Time
Assays
Activity Owner:
GMP/CMO Facility | New Product Introduction | 2014-03-19: NPI closeout
| Engineering Run | 2014-04-02: DS Engineering Run Prep and Execution; 2014-04-23: DS Engineering Batch Data Review/ BR Update
| GMP Runs | 2014-05-07: DS GMP Ref Std Batch; 2014-05-28: DS GMP Clinical Batch
| GMP Release | 2014-06-18: DS GMP Clinical Batch Release
Activity Owner:
Clinical
Activity Owner
Regulatory and Quality
Activity Owner
On Plan |  | 2013-11-27: Lifecycle Clinical Phases and Quality Risk Management Activities; 2014-01-22: © Thomas A. Little Consulting, 2011-2013
Late but will recover |  | 2013-12-04: Pre-Clinical
Late will not recover |  | 2013-12-11: Establish Target Product Profile and Define Critical Quality Attributes
Completed |  | 2013-12-11: Clinical Risk Assessment
Change in Stategy |  | 2013-12-11: Process and Method Risk Assessment
Material Selection Risk Assessment
TPP and CQA Risk Assessment
PreClinical QRM Report and associated risk reduction activities
Clinical Phase I
Reviews and Updates on all Clinical risk assessments.
Detailed process maps and FMEAs
Detailed assay process maps and FMEAs
Identification of CPP's and Initial Critical Process Parameter Risk Assessment
Initial Critical Method Risk Assessment
Facility, method, and/or process transfer risk assessment
QRM Report and associated risk reduction activities
Clinical Phase II
Updates on all Clinical and Phase I risk assessments.
Process and method optimization and design space with respect to CQAs and CPPs.
Critical parameter identification and control plan for process
Critical parameter control plan for analytical method
Facility, method, and/or process transfer risk assessment
QRM Report and associated risk reduction activities
Clinical Phase III
Updates on Clinical, Phase I and Phase II risk assessments.
Process and method design space confirmation with respect to CQAs and CPPs.
Detailed control strategy (process and method)
Facility, method, and/or process transfer risk assessment
QRM Report and associated risk reduction activities