## Project Charter
Resource Requirements |  |  |  | General Information |  |  | Tollgate Schedule
Project No: |  |  |  | Region: |  |  | Activity | Date
Project Name: |  |  |  | Business |  |  | Start
Green Belt or Black Belt: |  |  |  | Segment: |  |  | Define
Master Black Belt: |  |  |  | Business |  |  | Measure
Finance Partner: |  |  |  | Objective: |  |  | Analyze
Champion: | [6 empty] | Improve
|  | Hours |  |  |  |  | Control
Team Members: Name | Function | Per Week | Initials | Date: |  |  | Close
Project Definition
Business Case:
Project Problem Statement:
Project Objective Statement:
Project Scope/Limitations:
Project Goals, Targets and Timeframe:
Project Plan:
See page 2 of the project charter. Project Plan and Timeline
Expected Benefits: | [5 empty] | Time frame:
Hard Dollar Savings*:
Soft Dollar Savings*:
Strategic:
Other Benefits:
Stakeholder Approval
Champion: |  |  |  |  | Master Black Belt:
Name: |  |  |  |  | Name:
Signature: |  |  |  |  | Signature:
Functional Manager: |  |  |  |  | Black / Green Belt:
Name: |  |  |  |  | Name:
Signature: |  |  |  |  | Signature:
Finance: |  |  |  |  | Other:
Name: |  |  |  |  | Name:
Signature: |  |  |  |  | Signature:
Date:
© TLC, 2004-2013
*See Financial Analysis

## Problem Solving Plan
[6 empty] | Project Name: |  |  | Number:
| Site: |  |  | Location: |  |  |  | Revision Date:
Problem Statement:
Risk Assessment
Problem Containment:
Improvement Objective, Scope and Goals (timeframe):
| Metric(s): |  |  |  |  | Summary of Root Cause (Use Root Cause Analysis Summary Sheet)
Solution(s) to the Problem:
Tasks and Timelines
Steps | Activity |  |  |  |  | Assigned to: | Start Date: | End Date: | Status: | Review Date
1. Define &
Contain the
Problem
2. Measure
the Problem
3. Analyze the
Data and
Determine
Root Cause
4. Improve
Performance
5. Control and
Standardize
Improvements
| Team Members |  | Name |  | Hours per Week
|  | Team Leader: | [6 empty] | On Plan/On Schedule | On Plan
|  | Process Owner: | [6 empty] | Behind Plan, with effort can return to schedule | Behind
[9 empty] | Behind Plan and unable to meet schedule | Late
[9 empty] | Change of Plan | Change
[9 empty] | Task Completed | Complete
Executive Sponsor/Champion:
© Thomas A. Little Consulting 2005-2013
Metric Name:
| Measurement Frequency: | Daily
| Date: | Measure
1 | 2010-12-01 | 500
2 | 2010-12-02 | 425
3 | 2010-12-03 | 432
4 | 2010-12-04 | 342
5 | 2010-12-05 | 145
6 | 2010-12-06 | 123
7 | 2010-12-07 | 165
8 | 2010-12-08 | 134
9 | 2010-12-09
10 | 2010-12-10
11 | 2010-12-11
12 | 2010-12-12
13 | 2010-12-13
14 | 2010-12-14
15 | 2010-12-15
16 | 2010-12-16
17 | 2010-12-17
18 | 2010-12-18
19 | 2010-12-19
20 | 2010-12-20
21 | 2010-12-21
22 | 2010-12-22
23 | 2010-12-23
24 | 2010-12-24
25 | 2010-12-25
Formulas:
Site: = [Site:, row above]+1
Problem Solving Plan

## Timeline
[5 empty] | Start Date: |  | 2010-11-01
Use lines and or color bars to indicate start and stop dates for each activity
Phase: | Activity | Start Date | End Date | Assigned to: | 2010-11-01 | 2010-11-02 | 2010-11-03 | 2010-11-04 | 2010-11-05 | 2010-11-06 | 2010-11-07 | 2010-11-08 | 2010-11-09 | 2010-11-10 | 2010-11-11 | 2010-11-12 | 2010-11-13 | 2010-11-14 | 2010-11-15 | 2010-11-16 | 2010-11-17 | 2010-11-18 | 2010-11-19 | 2010-11-20 | 2010-11-21 | 2010-11-22 | 2010-11-23 | 2010-11-24 | 2010-11-25 | 2010-11-26 | 2010-11-27 | 2010-11-28 | 2010-11-29 | 2010-11-30 | 2010-12-01
1. Define and | bar: 2010-11-01 to 2010-11-05
Contain the | bar: 2010-11-03 to 2010-11-07
Problem
2. Measure the
Problem
3. Analyze the Data
and Determine
Root Cause
4. Improve
Performance
5. Standardize
and Control
Improvements
© Thomas A. Little Consulting 2004-2013
Timeline

## CQAs
CQA Risk notes
|  |  | Response (Y) | Risk | (high, medium or low)
If medium or high state why.
Measurement definition
| Product Requirement |  | Target
Company capability to perform CTQ?
|  |  | Specification Limits | (high, medium or low)
USL
LSL
Maximum allowable defect rate
|  |  | Response (Y) | Risk | (high, medium or low)
If medium or high state why.
Measurement definition
Product Name | Product Requirement |  | Target
Company capability to perform CTQ?
|  |  | Specification Limits | (high, medium or low)
USL
LSL
Maximum allowable defect rate
|  |  | Response (Y) | Risk | (high, medium or low)
If medium or high state why.
Measurement definition
| Product Requirement |  | Target
Company capability to perform CTQ?
|  |  | Specification Limits | (high, medium or low)
USL
LSL
Maximum allowable defect rate
|  |  | Response (Y) | Risk | (high, medium or low)
If medium or high state why.
Measurement definition
| Customer Requirement |  | Target
Company capability to perform CTQ?
|  |  | Specification Limits | (high, medium or low)
USL
LSL
Maximum allowable defect rate
|  |  | Response (Y) | Risk | (high, medium or low)
If medium or high state why.
Measurement definition
Customer Name | Customer Requirement |  | Target
Company capability to perform CTQ?
|  |  | Specification Limits | (high, medium or low)
USL
LSL
Maximum allowable defect rate
|  |  | Response (Y) | Risk | (high, medium or low)
If medium or high state why.
Measurement definition
| Customer Requirement |  | Target
Company capability to perform CTQ?
|  |  | Specification Limits | (high, medium or low)
USL
LSL
Maximum allowable defect rate
© TLC 2005-2013
Critical Quality Attributes (CQAs)

## Meeting Agenda
Team Name
Location:
Start and End Times:
Roles:
Facilitator:
Scribe:
Timekeeper:
Action Item Review
| Action Item | Who? | Due Date
1 | (list each one to be reviewed)
2
3
4
5
New Meeting Agenda Topics
| Description | Presenter | Time
1
2
3
4
5
Summary and Close
Summarize findings
Update action items
Plus/Delta on meeting
© TLC, 2004-2013
Meeting Agenda

## SIPOC
Who are the suppliers for our product or service? How capable are they in meeting our process requirements? | What must my suppliers provide to my process to meet my needs? What are the key inputs for each operation? | Determine the start and end points of the process associated with the problem and the major steps in the process. | What is the most appropriate end point for the process? What product or service does the process deliver to the customer? | Who are the customers for our product or service? What are their requirements for performance?
Process (High Level)
|  | Start Point: |  |  | Color code all inputs and outputs:
Routine quality problems
Occasional quality problems
No real quality problems
Suppliers | Input | Operation or Activity | Output | Customers
1.1 | a | 1 | a | 1.1
1.2 | b |  | b | 1.2
1.3 | c |  | c | 1.3
2.1 | a | 2 | a | 2.1
2.2 | b |  | b | 2.2
2.3 | c |  | c | 2.3
3.1 | a | 3 | a | 3.1
3.2 | b |  | b | 3.2
3.3 | c |  | c | 3.3
4.1 | a | 4 | a | 4.1
4.2 | b |  | b | 4.2
4.3 | c |  | c | 4.3
5.1 | a | 5 | a | 5.1
5.2 | b |  | b | 5.2
5.3 | c |  | c | 5.3
6.1 | a | 6 | a | 6.1
6.2 | b |  | b | 6.2
6.3 | c |  | c | 6.3
7.1 | a | 7 | a | 7.1
7.2 | b |  | b | 7.2
7.3 | c |  | c | 7.3
8.1 | a | 8 | a | 8.1
8.2 | b |  | b | 8.2
8.3 | c |  | c | 8.3
9.1 | a | 9 | a | 9.1
9.2 | b |  | b | 9.2
9.3 | c |  | c | 9.3
10.1 | a | 10 | a | 10.1
10.2 | b |  | b | 10.2
10.3 | c |  | c | 10.3
Add or remove rows as needed |  | End Point:
© Thomas A. Little Consulting 2005-2013

## Stakeholder Analysis
Project:
Date:
Project Leader:
| Name & | Function | Level of | Hours | Type/Level/ |  | Stakeholder Identified | How to Resolve
| Position | or | Participation | per | Frequency of | Initials | Issues or Problems | Issues or Problems
|  | Organization |  | Week | Communication | agreement
1
2
3
4
5
6
7
8
9
10
| Level of Participation: | [7 empty] | © TLC, 2004-2013
| Inform | Update on a need to know basis
| Consult | Occasionally obtain advise or expertise
| Include | Provides team members
| Involve | Participates in decision making
| Approve | Requires approval prior to implementation
Stakeholder Analysis

## Financial Analysis
Project Leader:
Project Name:
Date:
|  |  |  | Savings in Cost per Unit |  |  | Savings in Unit Volume
|  | Estimated unit |  | Estimated % | New estimated | Transaction rate or | % Savings | New Estimated | Annual New | Type of Savings |  | Dollar Savings
Estimate the cost of one unit or event |  | cost in USD ($) |  | Savings | Costs (one unit) | Unit Volumes (Annual) | in Unit Volume | Volume (Annual) | Costs (line item) | Hard or Soft? | Hard Savings | Soft Savings | Total Savings | Old Hard | Old Soft | New Hard | New Soft
| Direct Labor | 0.1 |  | 10% | 0.09 | 10950000 |  | 10950000 | 985500 | Soft | 0 | 109500 | 109500 | 0 | 1095000 | 0 | 985500
| Indirect Labor | 0.1 |  | 10% | 0.09 | 10950000 |  | 10950000 | 985500 | Hard | 109500 | 0 | 109500 | 1095000 | 0 | 985500 | 0
| Direct Materials | 0.1 |  | 10% | 0.09 | 10950000 |  | 10950000 | 985500 | Soft | 0 | 109500 | 109500 | 0 | 1095000 | 0 | 985500
| Indirect Materials | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Inventory | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Carrying Costs | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Facilities and Maintenance | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shipping Costs | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data Systems | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tooling | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (specify) | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (specify) | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (specify) | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Totals | 0.3 |  |  | 0.27 | 32850000 |  | 32850000 | 2956500 |  | 109500 | 219000 | 328500 | 1095000 | 2190000 | 985500 | 1971000
Hard Dollar Savings Summary |  |  |  | Soft Dollar Savings
Accumulated Annualized Cost (baseline) |  | 3285000 |  | Accumulated Annualized Cost (baseline) |  | 3285000
New Accumulated Annualized Cost (post project) |  | 3175500 |  | New Accumulated Annualized Cost (post project) |  | 3175500
Estimated % of Hard Dollar Savings |  | 3.333% |  | Estimated % of Soft Dollar Savings |  | 6.667%
Accumulated Annualized Savings |  | 109500 |  | Potential Annualized Savings |  | 219000
Project Cost |  |  |  | For Capital Only | Useful Life (years)
| Human resources | 68250 |  |  | 0
| Material costs | 0 |  | Annual Depreciation | Total Capital Costs
| Capital costs | 0 |  | 0 | 0
| Other costs | 0
| Total Project cost | 68250
Increased annualized revenue profits |  | 0
Estimated ROI (Hard) |  | 41250
Estimated Total ROI (Hard and Soft) |  | 260250
Fiscal period savings to be realized (PxxFYxx) |  | FY0X
Emphasis is on hard dollar savings as opposed to soft dollar savings.
Finance Approval, Finance Partner
© TLC, 2004-2013
Rev. 1.6
Financial Analysis

## Brainstorm
Potential Root Causes and Define Lines of Investigation
Problem Statement:
Information
Rank | Potential Root Cause | Supporting Data & Analysis?* | Source? | Who? | When?
Commitment to complete the investigation.
Possible investigation.
No commitment to investigate.
© Thomas A. Little Consulting 2005-2013
*Common types of data and analysis |  | Analysis description:
1 | Detailed Process Review | Careful walkthrough of the process step by step to determine the source, nature and frequency of the problem
2 | Process Mapping | Detailed process flow analysis to understand all the steps of the process, how the problem occurs and to document the process flow
3 | Visual Analysis | Visual examination of the problem and visual documentation such as digital photos and videos
4 | Cause and Effect (Event) Analysis | Examination of the potential relationship of factors and or event conditions on the problem
5 | Data Collection and Analysis | Measurement of performance from the product or process and an analysis of current data and associated factor effects
6 | Additional Tests and Experiments | Additional tests or experiments designed to understand the current situation and determine the root cause
Brainstorm Lines of Investigation

## Xs and Ys
Measure
Responses or Outputs (Ys) |  |  |  | Factors (Xs)
Dependent Variable | USL | LSL | Target | Independent Variable(s) | USL | LSL | Target
© Thomas A. Little Consulting 2005-2010
Measure Xs and Ys

## Data Collection Plan
Data Collection Plan
Define What to Measure |  |  | Define How to Measure |  |  | Who will do it? | Sampling Plan. The minimum representative sample of the population.
| Type of | Operational | Measurement | Data Tags Needed | Data Collection | Person(s) | What? | Where? | When? | How Many?
Measure | Measure | Definition | or Test Method | to Stratify the Data | Method | Assigned
Name of | X or Y | Clear definition of | Visual | Data tags are | Manual? | State | What | Location | How | The number
the condition | attribute or | the measurement | inspection | defined for the | Spreadsheet? | who has | measure is | for | often | of data
to be | discrete | defined in such a | or automated | measure. Such | Computer based? | the | being | data | the | points
measured. | data, | way as to achieve | test? | as: time, date, | etc. | responsibility? | collected | collection | data | collected
| product or | repeatable results | Test instruments | location, region, |  |  |  |  | is | per sample
| process | from multiple | are defined. | line, customer, |  |  |  |  | collected
| data. | observers. |  | buyer, operator,
|  |  | Procedures for | tester, etc.
data collection
are defined.
© Thomas A. Little Consulting 2005-2010
Measure Data

## Process Map
Use Excel for simple Process Maps and Visio Professional for more extensive process maps.
Organization | Operation Sequence or Time
Organization 1
Organization 2
Yes
No
Organization 3
© Thomas A. Little Consulting 2005-2010
Start
Operation 1
Correct?
Operation 2
Operation 2
End
Start or End
Operation
Wait or Delay
Decision
Storage
Process Map

## 5 Whys
1 | What is Wrong with current performance and Why?
2 | Why?
3 | Why?
4 | Why?
5 | Why?
Go further where required.
The problem may require more than 5 whys.
Add additional boxes and connections as needed.
Use JMP for more complicated 5 why analysis
5 Whys

## Cause & Effect
RCA Cause and Effect Table
Place an X in all boxes that may apply to the problem under investigation. Add additional issues that may apply based on brainstorming.
Measurement |  | Materials |  | Machine (Process and Test)
| Poor repeatability |  | Defective |  | Machine maintenance or calibration
| Poor reproducibility |  | Off-specification |  | Machine controls or lack of controls
| Poor accuracy |  | Contaminated |  | Machine fault or defect
| Poor stability |  | Improper storage conditions |  | Software or network fault
| Poor linearity |  | Labeling or identification |  | Machine related contamination
| Invalid measurement or test method |  | Incorrect amount or quantity |  | Machine tooling or fixtures
| Excessive test or measurement |  | Improper transportation or handling |  | Incorrect machine or tester
| Other (state potential cause) |  | Expiration date exceeded or unknown |  | Other (state potential cause)
Method |  |  | Problem with product design | Environment
| Incorrect definition |  | Wrong materials |  | Physical environment (ESD, lighting, etc.)
| Incorrect sequence |  | Other (state potential cause) |  | Security or safety systems
| Missing definitions, implicit rules | People |  |  | Distractions in the environment
| Poor process controls |  | Level of staffing |  | Particulates
| Poor measurement controls |  | Training |  | Contamination
| Lack of critical information |  | Competency or experience |  | Other (state potential cause)
| Incorrect information |  | Supervision
| Excessive queues or out-time |  | Conflicting goals
| Handling |  | Compliance with procedures
| Orientation |  | Personality issues
| Poor management of change |  | Physical ability or function
| Incorrect revision |  | Cognitive ability and function
| Other (state potential cause) |  | Knowledge deficit
Communication with peers or supervisor
Other (state potential cause)
© Thomas A. Little Consulting 2005-2010
Cause and Effect Analysis

## RCA Summary
Problem this analysis is to explain: | [8 empty] | Root Cause Analysis Conclusions:
30 day cycle time for customer quotes.
Completed Investigations | Completed |  | Investigation |  | Factor |  | Adj |  | % |  |  | Validation | Validation | Validation
| Review Date | Who? | Method | Conclusion* | Effect Size | Units | r2 | p value | Effect | Mechanism | Controllable (Y/N) | Method | Date | Results | Conclusion
Lack of Ownership | 2007-10-15 | Juan | Process Review | RC - Root Cause | 5 | days |  |  | 16.67% | No one schedules or assignes the quotes. | Y
|  |  |  | PC - Partial Contributor | 4 | days |  |  | 13.33%
|  |  |  | RC - Root Cause | 2 | days |  |  | 6.667%
|  |  |  | PC - Partial Contributor | 4 | days |  |  | 13.33%
|  |  |  | RC - Root Cause | 10 | days |  |  | 33.33%
|  |  |  | NC - Non Contributor | 0 | days |  |  | 0%
© Thomas A. Little Consulting 2005-2010 |  |  |  |  | 30 | days
| *Conclusion | [6 empty] | % Unexplained | 16.67%
| NC - Non Contributor |  | IDX - Data not available
| PC - Partial Contributor |  | RC - Root Cause
| ID - Insufficient Data |  | RCX - Root Cause Not Controllable
| *Common types of data and analysis |  | Analysis description:
1 | Detailed Process Review |  | Careful walkthrough of the process step by step to determine the source, nature and frequency of the problem
2 | Process Mapping (Lean Analysis) |  | Detailed process flow analysis to understand all the steps of the process, how the problem or waste occurs and to document the process flow
3 | Visual Analysis |  | Visual examination of the problem and visual documentation such as digital photos and videos
4 | Cause and Effect (Event) Analysis |  | Examination of the potential relationship of factors and or event conditions on the problem
5 | Data Collection and Analysis |  | Measurement of performance from the product or process and an analysis of current data and associated factor effects
6 | Additional Tests and Experiments |  | Additional tests or experiments designed to understand the current situation and determine the root cause
Root Cause Analysis Summary

## Solution Evaluation Form
Solution Evaluation Form
List Root Cause(s) | List Solutions | % Effect | Estimated Cost | Type of Solution | Complexity | Estimated Benefit | Risk* | Priority | Validation?
Root Cause 1 | Solutions 1
|  | % of | cost | Breakthrough or | time or | savings | High | Order | Need
|  | effect | of | Continuous | effort to | due to | Medium | of potential | to
|  | solution | solution | Improvement ? | implement | solution | or | solution | verify
|  | will have | implementation |  | short term? | or | Low | implmentation | effectiveness
|  | on the |  |  | long term? | improvement |  | 1st, 2nd, 3rd | of solution
|  | root cause |  |  |  | in customer
satisfaction
Root Cause 2
* Use Risk Assessment Form
© Thomas A. Little Consulting 2005-2010
Solutions

## Risk Assessment
Risk Assessment (Short Form)
List the Solution or | Failure Mode | Severity | Probability | Score | Action | Owner | Due
Major Elements of | (What can go wrong) | (1-10) | (10 is | (High scores | Plan |  | Date
Your Solution | List each failure mode | 10 is Worst | very probable) | need attention)
1.Solution
a)
b)
c)
2. Solution | a)
b)
c)
3. Solution | a)
b)
© Thomas A. Little Consulting 2005-2010
Risk

## Control Selection
Project: | [6 empty] | Date:
Project Leader:
Critical Project Ys, Xs, or Process Components that Require Controls
Type of control | Y1 | Y2 | Y3 | Y4 | Y5 | Y6
Measurement-Based Control | [6 empty] | Totals | Notes:
Change KPIs, Management Scorecards or Reviews | [6 empty] | 0
Statistical Process Control (SPC) | [6 empty] | 0
Documentation
Process flow diagrams | [6 empty] | 0
Product drawings, schematics | [6 empty] | 0
Process management/control plans | [6 empty] | 0
Written work procedures | [6 empty] | 0
Training documentation | [6 empty] | 0
Design out Product Problems
Design simplification or redesign | [6 empty] | 0
Mistake proofing (Poka Yoke) | [6 empty] | 0
Robust design concepts | [6 empty] | 0
Test and Inspection
Add additional tests (error prone) | [6 empty] | 0
Add inspection points/features (error prone) | [6 empty] | 0
Automated system checks | [6 empty] | 0
Periodic Checks
Scheduled maintenance | [6 empty] | 0
Scheduled calibration | [6 empty] | 0
Training and operator certification | [6 empty] | 0
Audits | [6 empty] | 0
Periodic management reviews | [6 empty] | 0
Incentives
Measures that are associated with a bonus | [6 empty] | 0
Measures that are associated with a penalty | [6 empty] | 0
Totals | 0 | 0 | 0 | 0 | 0 | 0
Not selected as a project control
| Ranking: 9 strongly supports controlling the Y or process component | 9 strongly supports controlling the Y or process component | [5 empty] | Possible project control
|  | 6 moderately supports controlling the Y or process component | [5 empty] | Selected project control
3 weakly supports controlling the Y or process component
0 does not support controlling the Y or process component
© Thomas A. Little Consulting, 2004-2010
Control Selection Matrix

## Translation and Standardization
|  | Project: |  |  |  |  | Date:
Project Leader:
Project ID | Solutions | What are the additional areas or products potentially impacted by the solution? | Standardization or Translation? | What needs to be translated? | Where does it need to be applied? | Risk assessment and or qualification required for translation? | Who will do it? | When? If phased when will the phases be completed? | Dollar benefits by area or product when fully completed?
S1
S2
S3
Standardization and Translation Plan

## Transfer Plan
| Project: |  |  | Date:
| Project Leader: |  |  | Long Term Owner:
Write a formal transfer plan to include the following:
Check |  | Determine the activities that need to continue once the team is dissolved:
|  | 1 | Define who is doing them now and who should be the long term owner.
|  | 2 | Determine who needs to do them in a sustaining mode.
|  | 3 | Assure ownership is mutually agreed upon by the individual and their immediate manager.
|  | 4 | The Manager/Owner is trained as to the specific responsibilities as a key part of the transfer plan.
|  | 5 | All new responsibilities are written into the individuals job description.
Define the set of tasks or systems that must be installed to completed prior to closing the project and backing out of work tasks.
1
2
3
4
5
What else is needed to make the solution effective and sustainable? Is the solution in the final form? Have all controls been implemented?
1
2
3
4
5
What are the changes in organizational responsibilities that need to occur?
1
2
3
4
5
What what else needs to be done to realize the benefits and savings?
|  | 1 | Redeploy personal
|  | 2 | Change supplier
|  | 3 | Change numbers (UPH, cost, inventory levels) in planning systems
|  | 4 | Eliminate inpsection or test
|  | 5 | Modify contracts
|  | 6 | Other changes needed to realize the savings
|  | 7 | Other changes needed to realize the savings
|  | 8 | Other changes needed to realize the savings
|  | 9 | Other changes needed to realize the savings
What are the other translation and standardization (fan out) activities that must occur to maximize the benefits?
1
2
3
4
5
6
7
8
9
Transfer Plan Checklist

## Final ROI
Project Leader:
Project Name:
Date:
|  |  |  | Savings in Cost per Unit |  |  | Savings in Unit Volume
|  | Estimated unit |  | Estimated % | New estimated | Transaction rate or | % Savings | New Estimated | Annual New | Type of Savings |  | Dollar Savings
Estimate the cost of one unit or event |  | cost in USD ($) |  | Savings | Costs (one unit) | Unit Volumes (Annual) | in Unit Volume | Volume (Annual) | Costs (line item) | Hard or Soft? | Hard Savings | Soft Savings | Total Savings | Old Hard | Old Soft | New Hard | New Soft
| Direct Labor | 0.1 |  | 10% | 0.09 | 10950000 |  | 10950000 | 985500 | Soft | 0 | 109500 | 109500 | 0 | 1095000 | 0 | 985500
| Indirect Labor | 0.1 |  | 10% | 0.09 | 10950000 |  | 10950000 | 985500 | Soft | 0 | 109500 | 109500 | 0 | 1095000 | 0 | 985500
| Direct Materials | 0.1 |  | 10% | 0.09 | 10950000 |  | 10950000 | 985500 | Soft | 0 | 109500 | 109500 | 0 | 1095000 | 0 | 985500
| Indirect Materials | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Inventory | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Carrying Costs | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Facilities and Maintenance | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Depreciation | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shipping Costs | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data Systems | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Tooling | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (specify) | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (specify) | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Other (specify) | 0 |  | 0% | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Totals | 0.3 |  |  | 0.27 | 32850000 |  | 32850000 | 2956500 |  | 0 | 328500 | 328500 | 0 | 3285000 | 0 | 2956500
Hard Dollar Savings Summary |  |  |  | Soft Dollar Savings
Accumulated Annualized Cost (baseline) |  | 3285000 |  | Accumulated Annualized Cost (baseline) |  | 3285000
New Accumulated Annualized Cost (post project) |  | 3285000 |  | New Accumulated Annualized Cost (post project) |  | 3285000
Estimated % of Hard Dollar Savings |  | 0% |  | Estimated % of Soft Dollar Savings |  | 10%
Accumulated Annualized Savings |  | 0 |  | Potential Annualized Savings |  | 328500
Project Cost |  |  |  | For Capital Only | Useful Life (years)
| Human resources | 68250 |  |  | 0
| Material costs | 0 |  | Annual Depreciation | Total Capital Costs
| Capital costs | 0 |  | 0 | 0
| Other costs | 0
| Total Project cost | 68250
Increased annualized revenue profits |  | 0
Estimated ROI (Hard) |  | -68250
Estimated Total ROI (Hard and Soft) |  | 260250
Fiscal period savings to be realized (PxxFYxx) |  | FY0X
Emphasis is on hard dollar savings as opposed to soft dollar savings.
Finance Approval, Finance Partner
© TLC, 2005-2010
Rev. 1.5
Final ROI