## Candidate Projects
Candidate Project Brainstorming
| Candidate Project Name | Estimate 1 unit cost | 1 unit savings | Annual Transaction Rate/Unit Volume | Estimated Project Cost | Estimated Annual Savings | Strategic Business Objective | Candidate Project Leader | Black/Green Belt
Areas with High Cost
1 | Energy use | 1000 | 500 | 2000 | 100000 | 900000
2 | Labor | $- | $- | - | $- | $-
3 | Materials | $- | $- | - | $- | $-
4 | Space | $- | $- | - | $- | $-
Painful Processes
5 |  | $- | $- | - | $- | $-
6 |  | $- | $- | - | $- | $-
7 |  | $- | $- | - | $- | $-
8 |  | $- | $- | - | $- | $-
Areas with Process Waste
9 | Over Production | $- | $- | - | $- | $-
10 | Waiting (lag time) | $- | $- | - | $- | $-
11 | Transporting | $- | $- | - | $- | $-
12 | Over Processing | $- | $- | - | $- | $-
13 | Inventory | $- | $- | - | $- | $-
14 | Motion | $- | $- | - | $- | $-
15 | Yield problems / defect rates too high | $- | $- | - | $- | $-
Cost of Quality
16 | Cost of Prevention | $- | $- | - | $- | $-
17 | Cost of Appraisal | $- | $- | - | $- | $-
18 | Cost of Internal failure | $- | $- | - | $- | $-
19 | Cost of External failure | $- | $- | - | $- | $-
Revenue Opportunities
20 | Increase revenue | $- | $- | - | $- | $-
21 | Reduction of revenue losses | $- | $- | - | $- | $-
22 |  | $- | $- | - | $- | $-
23 |  | $- | $- | - | $- | $-
Customer Satisfaction
24 |  | $- | $- | - | $- | $-
25 |  | $- | $- | - | $- | $-
26 |  | $- | $- | - | $- | $-
27 |  | $- | $- | - | $- | $-
Specific Strategic Objectives
28 |  | $- | $- | - | $- | $-
29 |  | $- | $- | - | $- | $-
30 |  | $- | $- | - | $- | $-
© TLC, 2003

## Project Selection
|  |  | Benefits |  | Business Goals |  |  | Risk |  |  | Type of
Rank | Potential Projects | Champion | Financial | Translatability | Defined | Customer Sat. | Clarity | Complexity | p(S) | Total | Benefit | Savings | Effort/Impact Analysis
| Weighting criteria |  | 5 | 1 | 1 | 2 | 1 | 2 | 5 |  | Hard/Soft/Cust.Sat. | Estimated ROI | Impact | Effort
1 |  |  | 3 | 4 | 3 | 7 | 3 | 3 | 3 | 39.22% |  |  | 0.44444 | 0.66667
2 |  |  | 9 | 5 | 7 | 3 | 8 | 5 | 8 | 79.08% |  |  | 0.77778 | 0.19444
3 |  |  | 3 | 4 | 9 | 8 | 4 | 6 | 3 | 49.02% |  |  | 0.54321 | 0.56944
4 |  |  | 9 | 6 | 4 | 7 | 8 | 4 | 7 | 78.43% |  |  | 0.85185 | 0.29167
5 |  |  | 9 | 9 | 7 | 5 | 2 | 3 | 4 | 64.71% |  |  | 0.87654 | 0.61111
6 |  |  | 3 | 3 | 3 | 3 | 9 | 6 | 6 | 50.98% |  |  | 0.33333 | 0.29167
7 |  |  | 2 | 2 | 3 | 2 | 9 | 9 | 8 | 56.21% |  |  | 0.23457 | 0.069444
8 | [9 empty] | 0% |  |  | 0 | 0
9 | [9 empty] | 0% |  |  | 0 | 0
10 | [9 empty] | 0% |  |  | 0 | 0
11 | [9 empty] | 0% |  |  | 0 | 0
12 | [9 empty] | 0% |  |  | 0 | 0
13 | [9 empty] | 0% |  |  | 0 | 0
14 | [9 empty] | 0% |  |  | 0 | 0
15 | [9 empty] | 0% |  |  | 0 | 0
16 | [9 empty] | 0% |  |  | 0 | 0
17 | [9 empty] | 0% |  |  | 0 | 0
18 | [9 empty] | 0% |  |  | 0 | 0
19 | [9 empty] | 0% |  |  | 0 | 0
20 | [9 empty] | 0% |  |  | 0 | 0
| Project name | Champion responsible for results | Hard dollar savings | Solutions are likely to be applicable across the site and the corporation | Currently defined business objective | Addresses a critical area associated with Customer Satisfaction | Clear problem definition with clear project boundaries | Complexity is a function of time to complete and the difficulty of the problem. | Probability of success
|  |  | 3 < $100k | 3 = local only | 3 = indirectly supports | 3 = indirectly supports | 3 = vaguely clear | 3 = high complexity | 3 = low
|  |  | 6 = $300k | 6 = some external | 6 = moderately supports | 6 = moderately supports | 6 = moderately clear | 6 = moderate complexity | 6 = moderate
|  |  | 9> $600K | 9 = all locations | 9 = directly supports | 9 = directly supports | 9 = clear boundaries | 9 = low complexity | 9 = high
© TLC, 2003 |  |  | When rating use: 9 = is very good, 6 = good, 3 = moderate and 0 poor | [11 empty] | Candidate Green Belt Projects
Candidate Black Belt Projects
Candidate Green Belt Projects
Candidate Black Belt Projects

## Project Charter
Resource Requirements |  |  |  | General Information |  |  | Tollgate Schedule
Project No: |  |  |  | Location: |  |  | Activity | Date
Project Name: |  |  |  | Business |  |  | Start
GB or BB: |  |  |  | Segment: |  |  | D
Master BB: |  |  |  | Business |  |  | M
Finance Partner: |  |  |  | Objective: |  |  | A
Champion: | [6 empty] | I
|  |  |  | Customer |  |  | C
Team Members: Name | Function | % Time | Initials | CTQ(s): |  |  | Close
Current
Process
|  |  |  | Capability: | Sigma, Cpk, DPMO, Cycle-time, etc.
Date:
Project Definition
Project Problem Statement:
Project Objective Statement:
Project Scope/Limitations:
Project Goals and Targets:
Project Plan:
See page 2 of the project charter. Project Plan and Timeline
Expected Benefits: | [5 empty] | Time frame:
Hard Dollar Savings*:
Soft Dollar Savings:
Strategic:
Other Benefits:
Stakeholder Approval
Champion: |  |  |  |  | Master Black Belt:
Name: |  |  |  |  | Name:
Signature: |  |  |  |  | Signature:
Functional Manager: |  |  |  |  | Black / Green Belt:
Name: |  |  |  |  | Name:
Signature: |  |  |  |  | Signature:
Finance: |  |  |  |  | Other:
Name: |  |  |  |  | Name:
Signature: |  |  |  |  | Signature:
Date:
© TLC, 2003
*See Financial Analysis
0.425

## Financial Analysis
|  |  | Analyst: | T. Cook
|  |  | Project Name: | Quote Cycle Time Reduction
|  |  | Date: | 200x
Estimate the cost of one unit or event |  | Estimated cost in dollars |  | Estimated % Savings | New estimated Costs
| Direct Labor | 2000 |  | 70% | 600
| Indirect Labor | 4000 |  | 70% | 1200
| Direct Materials | 0 |  | 0% | 0
| Indirect Materials | 0 |  | 0% | 0
| Inventory | 0 |  | 0% | 0
| Carrying Costs | 0 |  | 0% | 0
| Facilities & Maintenance | 0 |  | 0% | 0
| Durable Capital and Test Equipment | 0 |  | 0% | 0
| Shipping Costs | 0 |  | 0% | 0
| Data Systems | 0 |  | 0% | 0
| Overhead | 0 |  | 0% | 0
| Other (specify) | 0 |  | 0% | 0
| Summary single unit or event costs | 6000 |  | 70% | 1800
Transaction rate or unit volume frequency |  | 500 |  | 0% | 500
frequency per year |  | units or events per year |  | % savings frequency | new estimated frequency
Accumulated Annualized Cost |  | 3000000
Estimate the % of Savings |  | 70%
Accumulated Annualized Savings |  | 2100000
Project Cost
| Human resources | 125000
| Material costs | 0
| Other costs | 0
| Total Project cost | 125000
Increased annualized revenue profits |  | 500000
Estimated ROI |  | 2475000
Emphasis is on hard dollar savings as opposed to cost avoidance. Hard dollars are costs that are currently
being expended by the organization.
Finance Approval
© TLC, 2003
Rev. 1.2

## Stakeholder Analysis
|  |  |  | Project: | Quote Cycle Time Reduction
|  |  |  | Date: | 4/16/200x
|  |  |  | Black belt: | T. Cook
| Name & | Function | Level of | Hours | Type/Level/
| Position |  | Participation | per | Frequency of | Initials
|  |  |  | Week | Communication | agreement
1
| Fred T. | Materials | Inform | 1 | E-mail/project plan/weekly | ft
Manager
2
| Martha B. | Sales | Consult | 0.5 | E-mail/monthly or as needed | mb
Director
3
| Bill A. | Engineering | Approve | na | E-mail/project plan/weekly | ba
Manager
4
| Jack S. | Sales | Involve | 1 | E-mail/project plan/weekly | js
Manager
5
6
7
8
9
10
| Level of Participation: |  |  |  |  | © TLC, 2003
| Inform | Update on a need to know basis
| Consult | Occasionally obtain advise or expertise
| Include | Provides team members
| Involve | Participates in decision making
| Approve | Requires approval prior to implementation

## SIPOC
Who are the suppliers for our product or service? How capable are they in meeting our process requirements?
| What must my suppliers provide to my process to meet my needs? |  | What is the most appropriate end point for the process? What product or service does the process deliver to the customer?
Who are the customers for our product or service? What are their requirements for performance
Determine the start and end points of the process associated with the problem and the major steps in the process.
Suppliers | Input | Process (High Level) | Output | Customers
1 | 1 | Start Point: | 1 | 1
| 2 |  |  | 2
| 3 |  | 2 | 1
2 | 1 |  |  | 2
| 2 | Operation or Activity | 3 | 1
| 3 | 1 |  | 2
3 | 1 | 2 | 4 | 1
| 2 | 3 |  | 2
| 3 | 4 | 5 | 1
4 | 1 | 5 |  | 2
| 2 | 6 | 6 | 1
| 3 | 7 |  | 2
Add additional rows where needed |  | 8
9
10
11
End Point:
© TLC, 2003

## Six Sigma Project Plan
Project Name & Number:
| Site: |  | Location: |  |  | Revision Date:
Problem Statement:
Improvement Objective and Scope:
Goal and Targets
Metric(s)
Benefits
[5 empty] | Baseline | Goal | Improvement Goals
Date
Date
Date
Date
| Tasks and Timelines | [6 empty] | Project
Phases | Activity |  |  | Assigned to: | Start Date: | End Date: | Status: | Review Date
Define
Measure
Analyze
Improve
Control
Team Members
|  | Team Leader: |  |  |  |  | On Plan/On Schedule
|  | Team BB: |  |  |  |  | Behind Plan, with effort can return to schedule
|  | Team Members: |  |  |  |  | Behind Plan
Task Completed
Champion:
© TLC, 2003
| Data Interval | Metric
| 1 | 32
| 2 | 34
| 3 | 32
| 4 | 31
| 5 | 34
| 6 | 33
| 7 | 36
| 8 | 28
| 9 | 22
| 10 | 21
| 11 | 19
| 12 | 18
| 13 | 21
| 14 | 20
| 15 | 21
| 16 | 19
| 17 | 18
| 18 | 21
| 19 | 20
20
21
22

## Timeline
[5 empty] | Start Date: |  | 2003-06-10
Use lines and or color bars to indicate start and stop dates for each activity
Activity | Tasks | Start Date | End Date | Assigned to: | 2003-06-10 | 2003-06-17 | 2003-06-24 | 2003-07-01 | 2003-07-08 | 2003-07-15 | 2003-07-22 | 2003-07-29 | 2003-08-05 | 2003-08-12 | 2003-08-19 | 2003-08-26 | 2003-09-02 | 2003-09-09 | 2003-09-16 | 2003-09-23 | 2003-09-30 | 2003-10-07 | 2003-10-14 | 2003-10-21 | 2003-10-28 | 2003-11-04 | 2003-11-11 | 2003-11-18 | 2003-11-25 | 2003-12-02 | 2003-12-09 | 2003-12-16 | 2003-12-23 | 2003-12-30 | 2004-01-06
Define
Measure
Analyze
Improve
Control
© TLC, 2003

## Six Sigma Roadmap
Location:
|  |  |  | Enter Start Date: | 2003-05-10
Six Sigma Road Map & Timeline
| FY03 | 2003-05-10 |  |  | 2003-06-10 |  |  |  |  | 2003-07-11 |  |  |  | 2003-08-11 |  |  |  | 2003-09-11 |  |  |  |  | 2003-10-12 |  |  |  | 2003-11-12
| Wave I Six Sigma | 2003-05-10 | 2003-05-17 | 2003-05-24 | 2003-05-31 | 2003-06-07 | 2003-06-14 | 2003-06-21 | 2003-06-28 | 2003-07-05 | 2003-07-12 | 2003-07-19 | 2003-07-26 | 2003-08-02 | 2003-08-09 | 2003-08-16 | 2003-08-23 | 2003-08-30 | 2003-09-06 | 2003-09-13 | 2003-09-20 | 2003-09-27 | 2003-10-04 | 2003-10-11 | 2003-10-18 | 2003-10-25 | 2003-11-01 | 2003-11-08 | 2003-11-15 | 2003-11-22
1st Month - Planning | bar: 2003-05-10 to 2003-05-24
1.1 | Schedule SS Executive overview training | bar: 2003-05-10
1.2 | Six Sigma Executive overview training (½ day) | bar: 2003-05-10
1.3 | Establish clear financial goals and targets | bar: 2003-05-10
1.4 | Champion selection and schedule training | bar: 2003-05-17
1.5 | SS Champion training (2 days) | bar: 2003-05-24
1.6 | Project selection and estimated Wave I ROI | bar: 2003-05-24
1.7 | Black Belt and Green Belt selection | bar: 2003-05-24
1.8 | Software: JMP 5.0.1.2 and iGrafx process six sigma | bar: 2003-05-24
| 2nd Month - Begin Projects | 2003-11-01: Begin Wave II
2.1 | Six Sigma "Define" training (B&G Belt) 3 days | bar: 2003-06-07 to 2003-07-05
2.1.1 | Begin Champion review & tollgates (every 2 weeks) | 2003-06-14: *Review; 2003-06-28: Review; 2003-07-12: **Tollgate; 2003-07-26: Review; 2003-08-09: Tollgate; 2003-08-23: Review; 2003-09-06: Tollgate; 2003-09-20: Review; 2003-10-04: Tollgate; 2003-10-18: Review; 2003-11-01: Tollgate
2.1.2 | Begin Executive review of projects (monthly) | 2003-06-21: ***Status; 2003-07-19: Status; 2003-08-16: Status; 2003-09-13: Status; 2003-10-11: Status
2.2 | Six Sigma "Measure" training (B&G Belt) 4 days | bar: 2003-07-12 to 2003-08-02
2.3 | Six Sigma "Analyze" training (B&G Belt) 3 days | bar: 2003-08-09 to 2003-08-30
2.4 | Six Sigma "Improve" training (B&G Belt) 3 days | bar: 2003-09-06 to 2003-10-04
2.5 | Six Sigma "Control" training (B&G Belt) 3 days | 2003-11-01: End Wave I
2.6 | Final project report out and ROI determination | 2003-11-08: Final Report
2.9 | Realize savings from Wave I, savings fund Wave II | bar: 2003-11-08
3 | Select Master Black Belt (hire or assign) | bar: 2003-11-08
3.1 | Establish key metrics and scorecards if not present | bar: 2003-11-08
3.2 | Participants are "Certified" as Black or Green Belts | bar: 2003-11-08
| if projects are completed and meet savings req. | 2003-11-22: © TLC, 2003
|  | * Review: | Meeting with the Black Belt or Green Belt to evaluate and support project performance
|  | ** Tollgate: | Meeting with the Black Belt or Green Belt to review and complete "DMAIC" phase
|  | *** Status: | Executive review of projects with Champion
655 Old Orchard Danville

## Six Sigma Project Tracking
Six Sigma Wave: | Today's Date: | 2026-07-29 | Company:
Location:
Black Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 350000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Black Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2002-03-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1271.5714 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
302.7551 |  |  | Cell: | 350000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  |  | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1253.5714 | [5 empty] | 7 | Project Plan & Timeline
298.4694 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Black Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 350000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Black Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 350000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Black Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 350000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Green Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 250000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Green Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 250000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Green Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 250000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Green Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 250000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Green Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 250000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Green Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 | Customer CTQ(s) |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 250000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Green Belt | Contact Information |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
name | E-mail | Champion | Phone | Appointment | Project |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status |  | Deliverables | Status
Project Start Date: |  |  | Work: |  | Name | 1 |  |  | 8 | Project Metrics |  | 14 | Data Analysis Summary |  | 20 | List of Solutions and Risk |  | 26 | Transfer Plan
2003-04-16 | [5 empty] | 2 | Approved Charter |  | 9 | Data Collection Plan & Data |  | 15 | Process Map Analysis |  | 21 | Prioritized Solutions |  | 27 | Translation Opportunities
Time Spent on Project: | Address |  | Pager: |  |  | 3 | Financial Analysis |  | 10 | MSA where required |  | 16 | Visual Analysis Summary |  | 22 | Piloted Solution and Results |  | 28 | Control Plan
1215 |  |  |  | Expected Savings |  | 4 | Stakeholder Analysis |  | 11 | Process Capability |  | 17 | Root Cause Analysis |  | 23 | Solution Implementation Plan |  | 29 | Documentation of Results
289.2857 |  |  | Cell: | 250000 |  | 5 | SIPOC |  | 12 | Updated Project Goals |  | 18 | Root Cause Validation |  | 24 | Measures of Effectiveness |  | 30 | Final ROI of Project
Delta to Standard: | Building(s) |  |  |  |  | 6 | Detailed Process Map |  | 13 | Updated Project Plan |  | 19 | Updated Project Plan |  | 25 | Updated Project Plan
1197 | [5 empty] | 7 | Project Plan & Timeline
285 | [6 empty] | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete? |  |  | Tollgate Complete?
Project Timeline | Project Summary Table |  |  |  |  | Define |  |  | Measure |  |  | Analyze |  |  | Improve |  |  | Control
Reference Standard | [6 empty] | Deliverables | Days |  | Deliverables | Days |  | Deliverables | Days |  | Deliverables | Days |  | Deliverables | Days
Expected Number of | Number of Black Belt Projects | Average | Average | Expected Total Savings |  | 1 | Customer CTQ(s) | 2 | 8 | Project Metrics | 1 | 14 | Data Analysis Summary | 3 | 20 | List of Solutions and Risk | 2 | 26 | Transfer Plan | 1
Weeks to Completion | 5 | Expected | Expected |  |  | 2 | Approved Charter | 2 | 9 | Data Collection Plan & Data | 2 | 15 | Process Map Analysis | 3 | 21 | Prioritized Solutions | 2 | 27 | Translation Opportunities | 1
18 | Number of Green Belt Projects | Savings per | Savings per |  |  | 3 | Financial Analysis | 2 | 10 | MSA where required | 3 | 16 | Visual Analysis Summary | 3 | 22 | Piloted Solution and Results | 15 | 28 | Control Plan | 5
Months to Completion | 7 | Black Belt | Green Belt |  |  | 4 | Stakeholder Analysis | 2 | 11 | Process Capability | 15 | 17 | Root Cause Analysis | 2 | 23 | Solution Implementation Plan | 2 | 29 | Documentation of Results | 2
4.2857 | Total Number of Projects | 350000 | 250000 | 3150000 |  | 5 | SIPOC | 1 | 12 | Updated Project Goals | 1 | 18 | Root Cause Validation | 5 | 24 | Measures of Effectiveness | 1 | 30 | Final ROI of Project | 3
| 12 |  |  |  |  | 6 | Detailed Process Map | 5 | 13 | Updated Project Plan | 1 | 19 | Updated Project Plan | 1 | 25 | Updated Project Plan | 1
[6 empty] | 7 | Project Plan & Timeline | 1
[7 empty] | Weeks | 3 |  | Weeks | 4.6 |  | Weeks | 3.4 |  | Weeks | 4.6 |  | Weeks | 2.4
© TLC, 2003